## Sheet1
Module/Page | Task Description | Assigned by | Timeline
Collaboration/Innovation/Mentor/DPG/RDI tool/courses | Remove pagination and have have 'Load more' option | Satish | 14/06/2024 | Done | Fixed
Collaborations | Option for moderators to disable getting requests in private collaborations | Satish | 15/06/2024 | Done
All | Search button | Satish | 15/06/2024 | Done
| An option to upload document by the responsible person in workplan | Pratibha | 18/06/2024 | Done
Collaboration | Option to view for all and download for few | Pratibha | 18/06/2024 | Done(Download for all)
| Name could be a hashtag - Upon clicking name, all the collab contributions, innovation etc should be visible | Pratibha | TBD(with sathyan)
DINA | Add document' option | Pratibha | TBD(Indev team)
Agrotutor-WhatsApp | Delete learners in the whatspp userlist | Sherin | 18/06/2024 | Done
| Disable the courses that I'm a part of in the course list while enrolling for some other course | Sherin | 19/06/2024 | Done
General | Need user log | Chandra | 25/06/2024 | Done
General | innovation/resource/tool/course - No repetition of names | Pratibha | 26/06/2024 | Not implement in course
General | Total no. of innovation, collabs, tools, resources, events, metors etc visiblity on page | Pratibha | 26/06/2024 | Done but some fonts size is defferent like event and mentor. Pending in course.
Mentors | A new section that says - 'About'. This section will have a short bio of the mentor | Pratibha | 27/06/2024 | Done
collaboration | Leave collabration member and moderator | Pratibha | TBD(with sathyan)
notifcation | notification setting | Pratibha | TBD(with sathyan)
collabbration | view profile (Like member) | Pratibha | 28/06/2024

## Sheet2
Module | Issues
Forget Password | When we enter any email Id ehich is not registered validation text should be "Email ID does not exist".