## AIT-IndicativeWorkplan
Indicative workplan
Project Title : Mapping the plastic litter leaking into the waterways of Mekong countries and providing innovative solutions for efficient waste management.
Implementing Agency : Asian Institute of Technology
Duration / Period : 2 years 3 months (01/01/24 - 31/04/26)
Total budget: 609,106 USD
Activities | 2024 | [9 empty] | 2025 | [11 empty] | 2026
| Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May
Project personel (Manager, Coordinator, Finance Assistant) (Budget: 90,018 USD)
Project personel (Manager, Coordinator, Finance Assistant) | 2024 Mar: Budget: 33,340 USD (Year 1) + 40,008 USD (Year 2) + 16,670 (Year 3) = 90,018 USD
Output 0. Introduced the project goals, objectives, and activities - together with an indicative work plan to the national teams and stakeholders (Budget: 500 USD)
D0. Inception workshop and formation of national teams (online) | 2024 Mar: Budget: 500 USD
Output 1. Plastic Leakage Prevention (before-leakage activities) (Budget: 116,760 USD)
A1.Develop partnerships with local businesses and organizations to implement plastic reduction measures | 2024 Mar: Budget: 6,600 USD (Year 1)
A2. Conduct a survey to assess consumer behaviour and attitudes towards plastic use in a specific community. | 2024 Mar: Budget: 13,200 USD (Year 1)
A3. Design and conduct educational and awareness-raising activities targeting the public | 2024 Mar: Budget: 11,600 USD (Year 1)
A4. Carry out relevant capacity building for the ground survey. Carry out plastic waste flow analysis and plastic leakage hotspot mapping | 2024 Mar: Budget: 31,360 USD (Year 1) + 14,000 USD (Year 2) = 45,360 USD
A5. Outreach activities in waste segregation. | 2024 Mar: Budget: 24,000 USD (Year 1) + 16,000 USD (Year 2) = 40,000 USD
A6. Training district officers on zero-waste and plastic circularity, action plan development, and project evaluation. | 2024 Mar: Budget: 19,000 USD (Year 1) + 14,000 USD (Year 2) = 33,000 USD
Output 2. Plastic waste detection and monitoring methodology for the Mekong region is elaborated (Budget: 148,180 USD)
B1. Review the existing monitoring programme and methodology | 2024 Mar: Budget: 7,500 USD (Year 1)
B2. Develop a database for recording and analysis data on plastic waste | 2024 Mar: Budget: 13,000 USD (Year 1)
B3. Carry out the related technical capacity building to local technical partners for the AI plastic detection system. | 2024 Mar: Budget: 23,300 USD (Year 1)
B4. Set up monitoring equipment along the canals/rivers + continuous monitroing | 2024 Mar: Budget: 38,500USD (Year 1) + 21,000 USD (Year 2) = 59,500 USD
B5. Establish partnerships with local schools, community groups, and businesses to monitor and collect plastic waste in the project areas. | 2024 Mar: Budget: 15,280 USD (Year 1) + 21,400 USD (Year 2) = 36,680 USD
B6. Consult with the MRC on how to incorporate the project's methodologies into regional/national/local programme. | 2024 Mar: Budget: 8,200 USD (Year 2)
Output 3. Plastic waste collection (post-leakage activities) (Budget: 125,600 USD)
C1. Establish a network of collection points for plastic waste, such as clean-up stations or community drop-off, and public education | 2024 Mar: Budget: 23,520 USD (Year 1)
C2. Working with local district offices and pilot communities to improve waste collection system and infrastructure. | 2024 Mar: Budget: 26,400 USD (Year 2)
C3. Organize upcycling workshops using recycled plastics from the clean-up activities. | 2024 Mar: Budget: 23,400 USD (Year 2)
C4. Set up waste banks in local schools and provide monthly management coaching. | 2024 Mar: Budget: 28,720 USD (Year 1) + 23,560 USD (Year 2) = 52,280 USD
Output 4. Organised the evaluation workshop for the pilot implementation groups for sharing outputs and learning/working expereience, and lessons learned from the actual applications. (Budget: 42,294 USD)
D1. Hybrid Forum to reflect and synthesis the project activities including consultation for policy recommentation for capacity building activities. | 2024 Mar: Budget: 47,200 USD (Year 3)
D2. End of term evaluation | 2024 Mar: Budget: 8,000 USD (Year 3)