## Summary
BUDGET PROPOSAL
Project Title : Mapping the plastic litter leaking into the waterways of Mekong countries and providing innovative solutions for efficient waste management.
Implementing Agency : Asian Institute of Technology
Duration / Period : 2 years 3 months (01/03/24 - 31/05/26)
Budget Item | Description | Year 1 (10 months) | Year 2 (12 months) | Year 3 (5 months)
|  | Year 1 activities: D0, A1, A2, A3, A4, A5, A6, B1, B2, B3, B4, B5, C1, C4 | Year 2 activities: A4, A5, A6, B4, B5, B6, C2, C3, C4 | Year 3 activities: D1, D2
A | DIRECT COSTS:
1 | Personnel | 33340 | 40008 | 16670
2 | Consultancy services (Professional) | 185300 | 118000 | 22000
3 | Direct Supplies and Services | 18080 | 16600 | 10000
4 | Travel | 10920 | 0 | 19200
5 | Equipment | 18000 | 12000 | 0
6 | Other Direct Costs | 23780 | 21360 | 4000
| Sub total of Programme Cost | 289420 | 207968 | 71870
B | INDIRECT COSTS (7% management fee) | 20259.4 | 14557.76 | 5030.9
| Total (USD) | 309679.4 | 222525.76 | 76900.9
| TOTAL BUDGET (USD) | 609106.06
Note - If a cell is highlighted in red color, this means that the agreed % of that category has been overreached and it is applicable for budget items no 1, 5, and B
Activities | Year 1 | Year 2 | Year 3 | Total
Personnel | 33340 | 40008 | 16670 | 90018
A1 | 6600 | - | - | 6600
A2 | 13200 | - | - | 13200
A3 | 11600 | - | - | 11600
A4 | 31360 | 14000 | - | 45360
A5 | 24000 | 16000 | - | 40000
A6 | 19000 | 14000 | - | 33000
B1 | 7500 | - | - | 7500
B2 | 13000 | - | - | 13000
B3 | 23300 | - | - | 23300
B4 | 38500 | 21000 | - | 59500
B5 | 15280 | 21400 | - | 36680
B6 | - | 8200 | - | 8200
C1 | 23520 |  | - | 23520
C2 |  | 26400 | - | 26400
C3 |  | 23400 | - | 23400
C4 | 28720 | 23560 | - | 52280
D0 | 500 |  |  | 500
D1 |  |  | 47200 | 47200
D2 |  |  | 8000 | 8000
Total direct | 289420 | 207968 | 71870 | 569258
Indirect (7%) | 20259.4 | 14557.76 | 5030.9 | 39848.06
609106.06

## Activity Year1
BUDGET PROPOSAL
Project Title : Mapping the plastic litter leaking into the waterways of Mekong countries and providing innovative solutions for efficient waste management.
Implementing Agencies : AIT, ERIC, ISPONRE, GreenHub, RUPP, NUOL, COMPOSTED, TerraCycle Foundation, ClearRivers
Duration / Period : 2 years 3 months (01/03/24 - 31/05/26)
Year 1: Project Personnel Cost
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD)
A. Direct Costs
1. Personnel | Project Manager | 1429 | 10 | month | 1 | person | 14290
| Project Coordinator | 1380 | 10 | month | 1 | person | 13800
| Financial Assistant | 525 | 10 | month | 1 | person | 5250
Sub total of category 1 | [6 empty] | 33340
Total Direct Cost | [6 empty] | 33340
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 2333.8
TOTAL | [6 empty] | 35673.8
Year 1 Activity: D1. Inception workshop and formation of national teams (online)
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD)
A. Direct Costs
2. Consultancy services
2.1. | Consultant/Remuneration fee | 250 | 1 | days | 2 | person | 500
Sub total of category 2 | [6 empty] | 500
Total Direct Cost | [6 empty] | 500
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 35
TOTAL | [6 empty] | 535
Year 1 Activity: A1.Develop partnerships with local businesses and organizations to implement plastic reduction measures
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD)
A. Direct Costs
2. Consultancy services
2.1. | Consultant/Remuneration fee | 250 | 5 | day | 4 | person | 5000
Sub total of category 2 | [6 empty] | 5000
6. Other Direct Costs
6.1 | Local travel costs (4 countries) | 100 | 4 | day | 4 | person | 1600
Sub total of category 6 | [6 empty] | 1600
Total Direct Cost | [6 empty] | 6600
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 462
TOTAL | [6 empty] | 7062
Year 1 Activity: A2. Conduct a survey to assess consumer behaviour and attitudes towards plastic use in a specific community.
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD)
A. Direct Costs
2. Consultancy services
2.1. | Consultant/Remuneration fee | 250 | 10 | day | 4 | person | 10000
2.2. | Reports, communication materials etc. | 200 | 1 | day | 4 | country | 800
Sub total of category 2 | [6 empty] | 10800
6. Other Direct Costs
6.1 | Local travel costs (4 countries) | 200 | 3 | day | 4 | person | 2400
Sub total of category 6 | [6 empty] | 2400
Total Direct Cost | [6 empty] | 13200
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 924
TOTAL | [6 empty] | 14124
Year 1 Activity: A3. Design and conduct educational and awareness-raising activities targeting the public
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD)
A. Direct Costs
2. Consultancy services
2.1. | Consultant/Remuneration fee | 250 | 10 | day | 4 | person | 10000
2.2. | Reports, communication materials etc. | 200 | 1 | day | 4 | country | 800
Sub total of category 2 | [6 empty] | 10800
3. Direct Supplies and Services
3.1. | Design and printing of educational brochure | 200 | 1 | day | 4 | country | 800
Sub total of category 3 | [6 empty] | 800
6. Other Direct Costs
6.1
6.2
Sub total of category 6 | [6 empty] | 0
Total Direct Cost | [6 empty] | 11600
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 812
TOTAL | [6 empty] | 12412
Year 1 Activity: A4. Carry out relevant capacity building for the ground survey. Carry out plastic waste flow analysis and plastic leakage hotspot mapping
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD)
A. Direct Costs
2. Consultancy services
2.1. | Consultant/Remuneration fee | 250 | 30 | day | 2 | person | 15000
2.2. | Reports, communication materials etc. | 300 | 1 | day | 4 | country | 1200
2.3. | Airfare | 400 | 3 | ticket | 2 | person | 2400
2.4. | Ground transportation (VN,KH,LA) | 50 | 9 | day | 2 | person | 900
2.5. | Accommodation (2 nights in each 3 countries - VN, KH, LA) | 100 | 6 | night | 2 | person | 1200
Sub total of category 2 | [6 empty] | 20700
3. Direct Supplies and Services
3.1. | Meeting/training Package | 50 | 20 | person | 4 | country | 4000
Sub total of category 3 | [6 empty] | 4000
4. Travel (PIA)
4.1. | Airfare (Project Mangager & Coordinator) - KH,VN,LA | 400 | 3 | ticket | 2 | person | 2400
4.2. | Ground transportation | 50 | 9 | day | 2 | person | 900
4.3. | Accommodation | 100 | 6 | night | 2 | person | 1200
4.4. | Per Diem/Food | 50 | 9 | day | 2 | person | 900
4.5. | Travel insurance | 10 | 3 | ticket | 2 | person | 60
Sub total of category 4 | [6 empty] | 5460
6. Other Direct Costs
6.1 | Local travel costs (TH) | 100 | 3 | day | 4 | person | 1200
6.2
Sub total of category 6 | [6 empty] | 1200
Total Direct Cost | [6 empty] | 31360
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 2195.2
TOTAL | [6 empty] | 33555.2
Year 1 Activity: A5. Outreach activities in waste segregation.
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD)
A. Direct Costs
2. Consultancy services
2.1. | Consultant/Remuneration fee | 250 | 18 | day | 4 | person | 18000
Sub total of category 2 | [6 empty] | 18000
3. Direct Supplies and Services
3.1. | Meeting/training Package | 50 | 20 | person | 4 | country | 4000
Sub total of category 3 | [6 empty] | 4000
6. Other Direct Costs
6.1. | Local travel costs (4 countries) | 100 | 5 | day | 4 | person | 2000
Sub total of category 6 | [6 empty] | 2000
Total Direct Cost | [6 empty] | 24000
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 1680
TOTAL | [6 empty] | 25680
Year 1 Activity: A6. Training district officers on zero-waste and plastic circularity, action plan development, and project evaluation.
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD)
A. Direct Costs
2. Consultancy services
2.1. | Consultant/Remuneration fee | 250 | 15 | day | 4 | person | 15000
Sub total of category 2 | [6 empty] | 15000
3. Direct Supplies and Services
3.1. | Meeting/training Package | 50 | 10 | person | 4 | country | 2000
Sub total of category 3 | [6 empty] | 2000
6. Other Direct Costs
6.1. | Local travel costs (4 countries) | 100 | 5 | day | 4 | person | 2000
Sub total of category 6 | [6 empty] | 2000
Total Direct Cost | [6 empty] | 19000
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 1330
TOTAL | [6 empty] | 20330
Year 1 Activity: B1. Review the existing monitoring programme and methodology
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD)
A. Direct Costs
2. Consultancy services
2.1. | Consultant/Remuneration fee | 250 | 15 | days | 2 | person | 7500
Sub total of category 2 | [6 empty] | 7500
Total Direct Cost | [6 empty] | 7500
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 525
TOTAL | [6 empty] | 8025
Year 1 Activity: B2. Develop a database for recording and analysis data on plastic waste
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD)
A. Direct Costs
2. Consultancy services
2.1. | Consultant/Remuneration fee | 250 | 20 | day | 2 | person | 10000
Sub total of category 2 | [6 empty] | 10000
6. Other Direct Costs
6.1 | Mobile App development and Data visualization Platform (Dashboard) | 2000 | 1 | year | 1 | time | 2000
6.2. | Server setup, hosting, and maintenance | 1000 | 1 | year | 1 | time | 1000
Sub total of category 6 | [6 empty] | 3000
Total Direct Cost | [6 empty] | 13000
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 910
TOTAL | [6 empty] | 13910
Year 1 Activity: B3. Carry out the related technical capacity building to local technical partners for the AI plastic detection system.
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD)
A. Direct Costs
2. Consultancy services
2.1. | Consultant/Remuneration fee | 250 | 20 | day | 2 | person | 10000
2.2. | Airfare | 400 | 3 | ticket | 2 | person | 2400
2.3. | Ground transportation (VN,KH,LA) | 50 | 9 | day | 2 | person | 900
2.4. | Accommodation (2 nights in each 3 countries - VN, KH, LA) | 100 | 6 | night | 2 | person | 1200
Sub total of category 2 | [6 empty] | 14500
3. Direct Supplies and Services
3.1. | Meeting/training Package | 50 | 10 | person | 4 | country | 2000
Sub total of category 3 | [6 empty] | 2000
4. Travel (PIA)
4.1. | Airfare (Project Mangager & Coordinator) - KH,VN,LA | 400 | 3 | ticket | 2 | person | 2400
4.2. | Ground transportation | 50 | 9 | day | 2 | person | 900
4.3. | Accommodation | 100 | 6 | night | 2 | person | 1200
4.4. | Per Diem/Food | 50 | 9 | day | 2 | person | 900
4.5. | Travel insurance | 10 | 3 | ticket | 2 | person | 60
Sub total of category 4 | [6 empty] | 5460
6. Other Direct Costs
6.1 | Simultaneous translation (local interpreters) | 200 | 1 | day | 4 | country | 800
6.2 | Local travel costs (TH) | 135 | 4 | person | 1 | time | 540
Sub total of category 6 | [6 empty] | 1340
Total Direct Cost | [6 empty] | 23300
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 1631
TOTAL | [6 empty] | 24931
Year 1 Activity: B4. Set up monitoring equipment along the canals/rivers; on waste-collection boats; and on the waste collecion devices.
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD) | \
A. Direct Costs
2. Consultancy services
2.1. | Consultant/Remuneration fee | 250 | 45 | day | 2 | person | 22500
Sub total of category 2 | [6 empty] | 22500
5. Equipment (10% of the budget) | [6 empty] | 0
5.1. | AI-enabled CCTV | 1500 | 2 | unit | 4 | country | 12000
Sub total of category 5 | [6 empty] | 12000
6. Other Direct Costs
6.1 | Local travel costs (4 countries) | 100 | 4 | person | 1 | time | 400
6.2. | Server fee (CCTV's infrastructure) | 2000 | 1 | year | 1 | time | 2000
6.3. | Internet facility (CCTV) | 200 | 1 | year | 8 | unit | 1600
Sub total of category 6 | [6 empty] | 4000
Total Direct Cost | [6 empty] | 38500 | 680
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 2695
TOTAL | [6 empty] | 41195
Year 1 Activity: B5. Establish partnerships with local schools, community groups, and businesses to monitor and collect plastic waste in the project areas.
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD)
A. Direct Costs
2. Consultancy services
2.1. | Consultant/Remuneration fee | 250 | 10 | day | 4 | person | 10000
Sub total of category 2 | [6 empty] | 10000
3. Direct Supplies and Services
3.1. | Meeting/training Package | 50 | 10 | person | 4 | country | 2000
3.2. | Outreach materials (prints/media) | 220 | 4 | country | 1 | time | 880
Sub total of category 3 | [6 empty] | 2880
6. Other Direct Costs
6.1 | Local travel costs (4 countries) | 120 | 5 | day | 4 | person | 2400
Sub total of category 6 | [6 empty] | 2400
Total Direct Cost | [6 empty] | 15280
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 1069.6
TOTAL | [6 empty] | 16349.6
Year 1 Activity: C1. Establish a network of collection points for plastic waste, such as clean-up stations or community drop-off + public education
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD)
A. Direct Costs
2. Consultancy services
2.1. | Consultant/Remuneration fee | 250 | 20 | day | 4 | person | 20000
Sub total of category 2 | [6 empty] | 20000
3. Direct Supplies and Services
3.1. | Outreach materials (prints/media) | 200 | 4 | country | 1 | time | 800
3.2. | Signages for the communities | 200 | 4 | country | 1 | time | 800
Sub total of category 3 | [6 empty] | 1600
6. Other Direct Costs
6.1 | Local travel costs (4 countries) | 120 | 4 | day | 4 | person | 1920
Sub total of category 6 | [6 empty] | 1920
Total Direct Cost | [6 empty] | 23520
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 1646.4
TOTAL | [6 empty] | 25166.4
Year 1 Activity: C4. Set up waste banks in local schools and provide monthly management coaching.
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD)
A. Direct Costs
2. Consultancy services
2.1. | Consultant/Remuneration fee | 250 | 20 | day | 4 | person | 20000
Sub total of category 2 | [6 empty] | 20000
3. Direct Supplies and Services
3.1. | Outreach materials (prints/media) | 200 | 4 | country | 1 | time | 800
Sub total of category 3 | [6 empty] | 800
5. Equipment (10% of the budget) | [6 empty] | 0
5.1. | School support for setting up waste stations (baskets/tools) | 1500 | 4 | country | 1 | time | 6000
Sub total of category 5 | [6 empty] | 6000
6. Other Direct Costs
6.1 | Local travel costs (4 countries) | 120 | 4 | day | 4 | person | 1920
6.2.
Sub total of category 6 | [6 empty] | 1920
Total Direct Cost | [6 empty] | 28720
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 2010.4
TOTAL | [6 empty] | 30730.4

## Activity Year2
BUDGET PROPOSAL
Project Title : Mapping the plastic litter leaking into the waterways of Mekong countries and providing innovative solutions for efficient waste management.
Implementing Agencies : AIT, ERIC, ISPONRE, GreenHub, RUPP, NUOL, COMPOSTED, TerraCycle Foundation, ClearRivers
Duration / Period : 2 years 3 months (01/03/24 - 31/05/26)
Year 2: Project Personnel Cost
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD)
A. Direct Costs
1. Personnel | Project Manager | 1429 | 12 | month | 1 | person | 17148
| Project Coordinator | 1380 | 12 | month | 1 | person | 16560
| Financial Assistant | 525 | 12 | month | 1 | person | 6300
Sub total of category 1 | [6 empty] | 40008
Total Direct Cost | [6 empty] | 40008
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 2800.56
TOTAL | [6 empty] | 42808.56
Year 2 Activity: A4. Carry out plastic waste flow analysis and plastic leakage hotspot mapping (re-assessment)
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD)
A. Direct Costs
2. Consultancy services
2.1. | Consultant/Remuneration fee | 250 | 12 | day | 4 | person | 12000
Sub total of category 2 | [6 empty] | 12000
6. Other Direct Costs
6.1 | Domestic local transportation (field surveys, 4 countries) | 100 | 5 | day | 4 | person | 2000
Sub total of category 6 | [6 empty] | 2000
Total Direct Cost | [6 empty] | 14000
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 980
TOTAL | [6 empty] | 14980
Year 2 Activity: A5. Outreach activities in waste segregation.
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD)
A. Direct Costs
2. Consultancy services
2.1. | Consultant/Remuneration fee | 250 | 10 | day | 4 | person | 10000
Sub total of category 2 | [6 empty] | 10000
3. Direct Supplies and Services
3.1. | Meeting/training Package | 50 | 20 | person | 4 | country | 4000
Sub total of category 3 | [6 empty] | 4000
6. Other Direct Costs
6.1. | Domestic local transportation (4 countries) | 100 | 5 | day | 4 | person | 2000
Sub total of category 6 | [6 empty] | 2000
Total Direct Cost | [6 empty] | 16000
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 1120
TOTAL | [6 empty] | 17120
Year 2 Activity: A6. Training district officers on zero-waste and plastic circularity, action plan development, and project evaluation.
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD)
A. Direct Costs
2. Consultancy services
2.1. | Consultant/Remuneration fee | 250 | 10 | day | 4 | person | 10000
Sub total of category 2 | [6 empty] | 10000
3. Direct Supplies and Services
3.1. | Meeting/training Package | 50 | 10 | person | 4 | country | 2000
Sub total of category 3 | [6 empty] | 2000
6. Other Direct Costs
6.1. | Domestic local transportation (4 countries) | 100 | 5 | day | 4 | person | 2000
Sub total of category 6 | [6 empty] | 2000
Total Direct Cost | [6 empty] | 14000
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 980
TOTAL | [6 empty] | 14980
Year 2 Activity: B4. Set up monitoring equipment along the canals/rivers (continuous monitoring and reporting).
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD)
A. Direct Costs
2. Consultancy services
2.1. | Consultant/Remuneration fee | 250 | 30 | day | 2 | person | 15000
Sub total of category 2 | [6 empty] | 15000
6. Other Direct Costs
6.1 | Local travel costs (for onsite maintanence of CCTV units) | 150 | 4 | day | 4 | person | 2400
6.2. | Server fee (CCTV's infrastructure) | 2000 | 1 | year | 1 | time | 2000
6.3. | Internet facility (CCTV) | 200 | 1 | year | 8 | unit | 1600
Sub total of category 6 | [6 empty] | 6000
Total Direct Cost | [6 empty] | 21000
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 1470
TOTAL | [6 empty] | 22470
Year 2 Activity: B5. Establish partnerships with local schools, community groups, and businesses to monitor and collect plastic waste in the project areas.
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD)
A. Direct Costs
2. Consultancy services
2.1. | Consultant/Remuneration fee | 250 | 15 | day | 4 | person | 15000
Sub total of category 2 | [6 empty] | 15000
3. Direct Supplies and Services
3.1. | Meeting/training Package | 50 | 10 | person | 4 | country | 2000
3.2. | Outreach materials (prints/media) | 500 | 4 | country | 1 | time | 2000
3.3.
Sub total of category 3 | [6 empty] | 4000
6. Other Direct Costs
6.1 | Local travel costs (4 countries) | 100 | 6 | day | 4 | person | 2400
6.2.
Sub total of category 6 | [6 empty] | 2400
Total Direct Cost | [6 empty] | 21400
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 1498
TOTAL | [6 empty] | 22898
Year 2 Activity: B6. Consult with the MRC on how to incorporate the project's methodologies into regional/national/local programme.
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD)
A. Direct Costs
2. Consultancy services
2.1. | Consultant/Remuneration fee | 250 | 6 | day | 4 | person | 6000
Sub total of category 2 | [6 empty] | 6000
3. Direct Supplies and Services
3.1. | Meeting/training Package | 50 | 5 | person | 4 | country | 1000
Sub total of category 3 | [6 empty] | 1000
6. Other Direct Costs
6.1 | Local travel costs (4 countries) | 100 | 3 | day | 4 | person | 1200
6.2.
Sub total of category 6 | [6 empty] | 1200
Total Direct Cost | [6 empty] | 8200
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 574
TOTAL | [6 empty] | 8774
Year 2 Activity: C2. Working with local district offices and pilot communities to improve waste collection system and infrastructure.
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD)
A. Direct Costs
2. Consultancy services
2.1. | Consultant/Remuneration fee | 250 | 20 | day | 4 | person | 20000
Sub total of category 2 | [6 empty] | 20000
3. Direct Supplies and Services
3.1. | Outreach materials (prints/media - signages) | 1000 | 4 | country | 1 | time | 4000
Sub total of category 3 | [6 empty] | 4000
6. Other Direct Costs
6.1 | Local travel costs (4 countries) | 120 | 5 | day | 4 | person | 2400
Sub total of category 6 | [6 empty] | 2400
Total Direct Cost | [6 empty] | 26400
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 1848
TOTAL | [6 empty] | 28248
Year 2 Activity: C3. Organize upcycling workshops using recycled plastics from the clean-up activities.
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD)
A. Direct Costs
2. Consultancy services
2.1. | Consultant/Remuneration fee | 250 | 15 | day | 4 | person | 15000
Sub total of category 2 | [6 empty] | 15000
3. Direct Supplies and Services
3.1. | Outreach materials (prints/media) | 200 | 4 | country | 1 | time | 800
Sub total of category 3 | [6 empty] | 800
5. Equipment (10% of the budget) | [6 empty] | 0
5.1. | Miscellaneous tools and equipments for workshop activities | 1500 | 4 | country | 1 | time | 6000
…
Sub total of category 5 | [6 empty] | 6000
6. Other Direct Costs
6.1 | Local travel costs (4 countries) | 100 | 4 | day | 4 | person | 1600
6.2.
Sub total of category 6 | [6 empty] | 1600
Total Direct Cost | [6 empty] | 23400
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 1638
TOTAL | [6 empty] | 25038
Year 2 Activity: C4. Set up waste banks in local schools and provide monthly management coaching.
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD)
A. Direct Costs
2. Consultancy services
2.1. | Consultant/Remuneration fee | 250 | 15 | day | 4 | person | 15000
Sub total of category 2 | [6 empty] | 15000
3. Direct Supplies and Services
3.1. | Outreach materials (prints/media) | 200 | 4 | country |  |  | 800
Sub total of category 3 | [6 empty] | 800
5. Equipment (10% of the budget) | [6 empty] | 0
5.1. | Construction of waste stations (baskets/tools/metal frames) | 1500 | 4 | country | 1 | time | 6000
…
Sub total of category 5 | [6 empty] | 6000
6. Other Direct Costs
6.1 | Local travel costs (4 countries) | 110 | 4 | day | 4 | person | 1760
6.2.
Sub total of category 6 | [6 empty] | 1760
Total Direct Cost | [6 empty] | 23560
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 1649.2
TOTAL | [6 empty] | 25209.2

## Activity Year3
BUDGET PROPOSAL
Project Title : Mapping the plastic litter leaking into the waterways of Mekong countries and providing innovative solutions for efficient waste management.
Implementing Agencies : AIT, ERIC, ISPONRE, GreenHub, RUPP, NUOL, COMPOSTED, TerraCycle Foundation, ClearRivers
Duration / Period : 2 years 3 months (01/03/24 - 31/05/26)
Year 3: Project Personnel Cost
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD)
A. Direct Costs
1. Personnel | Project Manager | 1429 | 5 | month | 1 | person | 7145
| Project Coordinator | 1380 | 5 | month | 1 | person | 6900
| Financial Assistant | 525 | 5 | month | 1 | person | 2625
Sub total of category 1 | [6 empty] | 16670
Total Direct Cost | [6 empty] | 16670
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 1166.9
TOTAL | [6 empty] | 17836.9
Year 3 Activity: D1. Hybrid Forum to reflect and synthesis the project activities including consultation for policy recommentation for capacity building activities.
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD)
A. Direct Costs
2. Consultancy services
2.1. | Consultant/Remuneration fee | 250 | 3 | day | 12 | person | 9000
2.2. | Reports, communication materials etc. | 300 | 2 | day | 1 | time | 600
2.3. | Airfare | 400 | 1 | ticket | 8 | person | 3200
2.4. | Ground transportation | 150 | 12 | person | 1 | time | 1800
2.5. | Accommodation | 100 | 2 | night | 12 | person | 2400
Sub total of category 2 | [6 empty] | 17000
3. Direct Supplies and Services
3.1. | Meeting/training Package | 50 | 50 | person | 2 | day | 5000
3.2. | Media (design, prints, photographer, technical team) | 1000 | 2 | day | 1 | time | 2000
3.3. | Other expenditures under Category 3 | [5 empty] | 0
Sub total of category 3 | [6 empty] | 7000
4. Travel (Participants/stakeholders, Final workshop in Bangkok, Thailand)
4.1. | Airfare | 400 | 1 | ticket | 20 | person | 8000
4.2. | Ground transportation | 150 | 20 | person |  |  | 3000
4.3. | Accommodation | 100 | 2 | night | 20 | person | 4000
4.4. | Per Diem/Food | 50 | 4 | day | 20 | person | 4000
4.5. | Travel insurance | 10 | 20 | person | 1 | time | 200
Sub total of category 4 | [6 empty] | 19200
6. Other Direct Costs
6.1 | Local travel costs (Thailand) | 100 | 2 | day | 20 | person | 4000
Sub total of category 6 | [6 empty] | 4000
Total Direct Cost | [6 empty] | 47200
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 3304
TOTAL | [6 empty] | 50504
Year 3 Activity: D2. End of term evaluation
Budget Line | Description | Unit Cost (USD) | Quantity 1 | Unit 1 | Quantity 2 | Unit 2 | Total Cost (USD)
A. Direct Costs
2. Consultancy services
2.1. | Consultant/Remuneration fee | 250 | 5 | day | 4 | person | 5000
Sub total of category 2 | [6 empty] | 5000
3. Direct Supplies and Services
3.1. | Report translation (350 words/page) | 15 | 50 | pages | 4 | languages | 3000
Sub total of category 3 | [6 empty] | 3000
6. Other Direct Costs
6.1
Sub total of category 6 | [6 empty] | 0
Total Direct Cost | [6 empty] | 8000
B. Indirect Costs
1. Management fee (7% of the total direct cost budget)
Sub total of Indirect Cost | [6 empty] | 560
TOTAL | [6 empty] | 8560